## Checklist
Object Detection with Jetson Nano integrated in a Kuka KR6
Name, Vorname |  |  |  | cc: Firmenbetreuer
Matr.-Nr | <1234567> |  |  | Projektpartner
Erstprüfer
Checklist
update every day!
No. | Topic | done | date
First two weeks
1 | read ProjectManagement/BestPractice.pdf | 1st Week | TRUE
2 | fulfill author.xlsx |  | FALSE
3 | Install TeXLive |  | TRUE
4 | install TeXStudio |  | TRUE
5 | install Sumatrapdf |  | TRUE
6 | configure TeXStudio |  | TRUE
7 | test template report |  | FALSE
8 | test template poster |  | FALSE
9 | test template Presentations/template |  | FALSE
10 | install doxygen |  | TRUE
11 | readme.md |  | FALSE
12 | literature research | 2nd week | FALSE
13 | bib file |  | FALSE
14 | bibliography |  | FALSE
15 | pdf files |  | FALSE
16 | presentation "Literature" |  | FALSE
17 | challenges with citations |  | FALSE
18 | write n introduction with citations |  | FALSE
19 | presentation "Introduction" |  | FALSE
20 | project plan | 3rd week | FALSE
21 | fulfill the list "Resulting Objects" |  | FALSE
22 | presentation "Project Plan" |  | FALSE
23 | Readme.md |  | FALSE
Processing the project
24 | update project plan | 4th week | FALSE
25 | update the list "Resulting Objects" |  | FALSE
26 | presentation "Project Plan" II |  | FALSE
27 | rename all tex files along the project plan |  | FALSE
28 | delete or add additional TeX or Python projects, e.g. Manual |  | FALSE
29 | List of Material |  | FALSE
30 | Manual |  | FALSE
31 | domain knowledge | 5th week | FALSE
32 | algorithm |  | FALSE
33 | tools |  | FALSE
34 | methodology |  | FALSE
35 | database | 6th week | FALSE
36 | database description |  | FALSE
37 | database discussion |  | FALSE
38 | Homework "Literature" | 7th week | FALSE
39 | Homework "John Ousterhout" |  | FALSE
40 | updated README.md |  | FALSE
41 | updated Project plan | 8th weeek | FALSE
42 | updated Resulting objects |  | FALSE
43 | Evaluation |  | FALSE
44 | Validation |  | FALSE
45 | Homework "UpdatedLiterature" | 9th week | FALSE
46 | Development structure |  | FALSE
47 | Development Environment |  | FALSE
48 | From Development to Deployment | 10 th weeek | FALSE
49 | Flow Chart |  | FALSE
50 | tests |  | FALSE
Final stage
51 | check: all website as pdf-file? |  | FALSE
52 | check: all pdfs in the folder Documents? |  | FALSE
53 | check: all images okay? |  | FALSE
54 | check spelling |  | FALSE
55 | check: poster? |  | FALSE
56 | print poster |  | FALSE
57 | check: GitHub project |  | FALSE
58 | ready minimal one day before deadline |  | FALSE
59
60
61
62

## Projekt Plan V1.0 (deut.)
Das Liebesleben der Maikäfer bei Nacht
|  | KW | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | ... | 26 | 27 | ... | 30
|  | lfd. Woche | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | ... | 16 | 17 | ... | 20
TP-Nr. | TP-Name | Dauer
1 | Einarbeitung / Literatur | 2.5
2 | ... | 1
3 | ... | ...
4 |  | 2
5 |  | ...
6
7
8
9
10
11
12
13
14 | Verfassen PA / BT / DA / MT | ...
15 | Durchsicht | 2
16 |  | 1.5
17 | Kolloquium | 1
| Urlaub / Feiertage | [5 empty] | Geburt |  |  | Ostern |  | Pfingsten
| Anmeldung / Abgabe | [7 empty] | 34. März |  |  |  |  | 34. Juli
Besprechungen
PJ = Projekt
| TP = Teilprojekt | [8 empty] | x = f(Studiengang)
Anmeldung
Abgabe
Hermann Meyer
Matr.-Nr. 1112569
7. Sem PVT
Version: 1.3 / 29.02.2025
Persönliche Daten
Vorläufiger Titel
der Arbeit
Nr. des Teilprojektes
(10 - 20 incl. Kolloquium)
Bezeichnung des Teilprojektes
Kalenderwoche des Jahres = zeitl. Lage
Laufende Woche der Arbeit seit Start => Dauer
planbare Ausfallzeiten
(selbst, Partner, Prüfer)
Anmeldetermin = gepl. Abgabetermin
abzgl. x Monate (für BT/DA/MT)
geplanter Abgabetermin
Teilprojekt
Balkenlänge = geschätzte Dauer; kleinste Einheit = 0,5 Wochen
subjektiver Abarbeitungzustand des TP bei korrelierender Besprechung
gepl. Besprechungstermin mit Erstprüfer
Planungsstand des Projektplans (Version, Datum)
spontan + intuitiv geschätzte Dauer des TP;
kleinste Einheit = 0,5 Wochen
Projektplan-Muster für eine Projektarbeit (PA) / Bachelor Thesis (BT) / Diplomarbeit (DA) / Master Thesis (MT)
cc: - Firmen-Betreuer
- PJ-Partner
- Erstprüfer
Empfänger
des PJ-Plans
Plan hier: Bearbeitung wegen Auszeit unterbrechen
Plan hier: Bearbeitung trotz Feiertage fortführen
1
2
2
3
5
4
6
7
8
9
10v
11v

## Project Plan V1.0 (eng.)
The Love Life of Cockchafers at Night
|  | Week of Year | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | ... | 35 | 36 | ... | 39
|  | Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | ... | 26 | 27 | ... | 30
SP No. | SP's Title | Duration
1 | Informative activities / literature | 2.5
2 | ... | 1
3 | ... | ...
4 |  | 2
5 |  | ...
6
7
8
9
10
11
12
13
14 | Writing of thesis | ...
15 | First checking through by examiner | 2
16 | Optimization | 1.5
17 | Colloquium | 1
| Vacation / holidays | [5 empty] | Birth |  |  | Easter |  | Pentecost
| Enrolement / Submission | [7 empty] | March 34 |  |  |  |  | July 34
Meetings
SP = Sub-project
x = f(course of study)
Enrolement
Submission
Hermann Meyer
Matr.-Nr. 1112569
7. Sem PVT
Version: 1.0 / 29.02.2025
Personal Data
Preliminary title
of thesis
SP's number
(10 - 20 SPs incl. Colloquium)
SP's title
Week of year
Weeks since start of project => duration
schedulable time outs
(causes: yourself, partners, examiner, ..)
Date of enrolement = scheduled date of submission minus x months
scheduled date of submission
SP
Length of bar = estimated duration; smallest unit = 0.5 week
Actual state of SP's completion at time of corresponding meeting
(subjective estimation)
Scheduled meeting with first examiner
Project plan of (version / date)
Duration of SP estimated in the beginning
(spontaneously and intuitivly)
smallest unit = 0,5 week
Template for Project Plan of Master's Thesis
cc: - Contact person in company
- Project partner
- First examiner
Receivers of this project plan
Scheduled interruption of work
Scheduled to continue work despite of holiday
Colloquium
1
2
2
3
5
4
6
7
8
9
10v
11v

## Resulting objects
Object Detection with Jetson Nano integrated in a Kuka KR6
Name, Vorname |  |  |  | cc: Firmenbetreuer
Matr.-Nr | <1234567> |  |  | Projektpartner
Erstprüfer
List of all Resulting Objects
Subtask | Resulting objects | done | date
Literature | List of keywords
Brief description of the sources
bib file
Bibliography in the report
pdf documents
quality check
…
Projectplan-Project (10credits) in Master Course "Business Intelligence and Data Analytics"